## BHI
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED |  |  |  |  | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIPMENT | QTY | SHIP | SHIP |  | FREIGHT | FORWARDER | FORWARDER
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | CFM. DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | CFM. DATE | NO | QTY | DATE | SV | ID | SHIPPED | DATE | VIA | ETA | FORWARDER | SHIPMENT ID | ID NO.
BHIDEU | 4511002275 | 10 | C53496 | HEAD DSCHG BOLT-ON MACH | 2020-04-09 | 8 | Air | 2020-04-10 | 2020-05-10 | Tanuja Rana | LT | 0 | DELIVERED |  | 2020-05-10 |  |  |  |  | YR2006 | 8 | 2020-06-08 | AIR
Formulas:
UPDATED = IF([ORIG.]="","",[ORIG.])

## GE
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED | [5 empty] | ORIG. CFM. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | 1ST SHIP | 1ST SHIP | 1ST SHIP | 1ST SHIP | 2ND SHIP | 2ND SHIP | 2ND SHIP | 2ND SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | EXW DATE | BUYER | SUPPLIER | BALANCE | STATUS | +/- DAY | EXW DATE | NO | QTY | DATE | SV | NO | QTY | DATE | SV | NO | QTY | DATE | SV | NO | QTY | DATE | SV | NO | QTY | DATE | SV | PO # | LN #

## BC
Cust ID | PO # | LN # | P/N | DESCRIPTION | ORDER | PO | SHIP | REQ. | UPDATED | BUYER | SUPPLIER | BALANCE | STATUS | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIP | SHIPPED | SHIP | SHIPPED | FF | Tracking | Ship Date | 3RD SHIP | 3RD SHIP | 3RD SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP
[5 empty] | DATE | QTY | VIA | DATE | CFM. DATE |  |  |  |  | DATE | CFM. DATE | NO | QTY | DATE | SV | ID | QTY | DATE | VIA |  |  |  | QTY | DATE | SV | NO | QTY | DATE | SV
BC | BCB0722 | 1 | 22027-02 | DIAPHRAGM NYLON REINFORCED NITRILE | 2022-07-22 | 1000 | Sea | 2022-08-15 | 2022-08-15 | Bob Craven | HIT | 1000 | Open |  | 2022-08-15 | 0 | 0 | 0 | 0
BC | BCB0707 | 1 | 22056 | NAME PLATE | 2022-07-07 | 1000 | Sea | 2022-07-30 | 2022-08-15 | Bob Craven | HIT | 1000 | Open |  | 2022-08-15 | 0 | 0 | 0 | 0
BC | 26177 | 1 | 22093 | VALVE BODY SAMPLE | 2022-03-22 | 8 | Exp | 2022-04-30 | 2022-05-30 | Bob Craven | XY | 8 | Open |  | 2022-05-30 | 0 | 0 | 0 | 0
BC | 26177 | 2 | 22093 | VALVE BODY | 2022-03-22 | 250 | Sea | 2022-05-30 |  | Bob Craven | XY | 250 | Open |  |  | 0 | 0 | 0 | 0
BC | 26175 | 1 | 22092 | VALVE BODY MACH SAMPLE | 2022-03-22 | 8 | Exp | 2022-04-30 | 2022-05-30 | Bob Craven | XY | 8 | Open |  | 2022-05-30 | 0 | 0 | 0 | 0
BC | 26175 | 2 | 22092 | VALVE BODY MACH | 2022-03-22 | 250 | Sea | 2022-05-30 |  | Bob Craven | XY | 250 | Open |  |  | 0 | 0 | 0 | 0
BC | 45265 | 1 | 22022 | BODY F 1/4" PK OFF W/T | 2022-03-17 | 720 | Sea | 2022-03-30 | 2022-04-30 | Bob Craven | XY | -20 | Delivered |  | 2022-04-30 | XY2207 | 740 | 2022-05-10 | S | XY2207 | 740 | 2022-05-10 | S
BC | 45265 | 2 | 22023 | 1/4" PACKING NUT W/T | 2022-03-17 | 720 | Sea | 2022-03-30 | 2022-04-30 | Bob Craven | XY | -20 | Delivered |  | 2022-04-30 | XY2207 | 740 | 2022-05-10 | S | XY2207 | 740 | 2022-05-10 | S
BC | 45265 | 3 | 22024 | 1/4" PACKING RING W/T | 2022-03-17 | 720 | Sea | 2022-03-30 | 2022-04-30 | Bob Craven | XY | -20 | Delivered |  | 2022-04-30 | XY2207 | 740 | 2022-05-10 | S | XY2207 | 740 | 2022-05-10 | S
BC | 45265 | 4 | 22030 | BODY W/T | 2022-03-17 | 750 | Sea | 2022-03-30 | 2022-04-30 | Bob Craven | XY | -67 | Delivered |  | 2022-04-30 | XY2207 | 817 | 2022-05-10 | S | XY2207 | 817 | 2022-05-10 | S
BC | 45265 | 5 | 22031 | NUT PACKING W/T | 2022-03-17 | 750 | Sea | 2022-03-30 | 2022-04-30 | Bob Craven | XY | -67 | Delivered |  | 2022-04-30 | XY2207 | 817 | 2022-05-10 | S | XY2207 | 817 | 2022-05-10 | S
BC | 3102022 | 1A | 22066 | MICROVALVE ASSY W/T | 2022-03-10 | 500 | Sea | 2022-04-30 | 2022-04-30 | Bob Craven | XY | 0 | Delivered |  | 2022-04-30 | XY2207 | 500 | 2022-05-10 | S | XY2207 | 500 | 2022-05-10 | S
BC | 3102022 | 1B | 22066 | MICROVALVE ASSY W/T | 2022-03-10 | 400 | Sea | 2022-04-30 | 2022-05-30 | Bob Craven | XY | 0 | Delivered |  | 2022-04-30 | XY2208 | 400 | 2022-05-30 | S | XY2208 | 400 | 2022-05-30 | S
BC | 3102022 | 1C | 22066 | MICROVALVE ASSY W/T | 2022-03-10 | 100 | Exp | 2022-04-30 | 2022-06-08 | Bob Craven | XY | 0 | delivered |  | 2022-04-30 | XY2210 | 100 | 2022-06-08 | E | XY2210 | 100 | 2022-06-08 | E
BC | 3102022 | 2 | 22066 | MICROVALVE ASSY W/T | 2022-03-10 | 1000 | Sea | 2022-05-30 | 2022-05-30 | Bob Craven | XY | -100 | Delivered |  | 2022-05-30 | XY2208 | 1100 | 2022-05-30 | S | XY2208 | 1100 | 2022-05-30 | S
BC | 45264 | 1 | 22055 | CONTROL BOX AL SET | 2022-01-20 | 250 | Sea | 2022-01-30 | 2022-06-30 | Bob Craven | HIT | 250 | Open |  | 2022-04-15 | 0 | 0 | 0 | 0
BC | 45264 | 2 | 22055 | CONTROL BOX AL SET | 2022-01-20 | 250 | Sea | 2022-03-30 | 2022-06-30 | Bob Craven | HIT | 250 | Open |  | 2022-04-15 | 0 | 0 | 0 | 0
BC | 45264 | 3 | 22057 | U RETAINER | 2022-01-20 | 250 | Sea | 2022-01-30 | 2022-02-28 | Bob Craven | XY | -45 | Shipped |  | 2022-02-28 | XY2205 | 295 | 2022-03-15 | S | XY2205 | 295 | 2022-03-15 | S
BC | 45264 | 4 | 22057 | U RETAINER | 2022-01-20 | 250 | Sea | 2022-03-30 | 2022-03-30 | Bob Craven | XY | -45 | Shipped |  | 2022-03-30 | XY2205 | 295 | 2022-03-15 | S | XY2205 | 295 | 2022-03-15 | S
BC | 45264 | 5 | 22058 | L CONNECTOR | 2022-01-20 | 250 | Sea | 2022-01-30 | 2022-06-30 | Bob Craven | HIT | 250 | Open |  | 2022-04-15 | 0 | 0 | 0 | 0
BC | 45264 | 6 | 22058 | L CONNECTOR | 2022-01-20 | 250 | Sea | 2022-03-30 | 2022-06-30 | Bob Craven | HIT | 250 | Open |  | 2022-04-15 | 0 | 0 | 0 | 0
Formulas:
UPDATED = IF([ORIG.]="","",[ORIG.])
CNTRCT = [SHIP]

## WMK
Cust ID | PO # | LN # | P/N | DESCRIPTION | ORDER | PO | SHIP | REQ. | UPDATED | BUYER | SUPPLIER | BALANCE | STATUS | DELIVERY | ORIG CFM | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIP | SHIPPED | SHIP | SHIPPED | FF | TRACKING | SHIP
[5 empty] | DATE | QTY | VIA | DATE | EXW DATE |  |  |  |  | DATE | EXW DATE | NO | QTY | DATE | SV | ID | QTY | DATE | VIA |  |  | DATE
WMKHOU | 999117336 | 1 | 1121900 | ADJ. SCREW, 1"RV | 2022-08-04 | 500 | Exp | 2022-08-12 | 2022-08-15 | Melissa Gonzalez | HIT | 0 | Delivered |  | 2022-08-15 | EWL2220 | 500 | 2022-08-14 | E | EWL2220 | 500 | 2022-08-14 | E | UPS
WMKHOU | 999117204 | 1 | 1156157 | BODY PILOT | 2022-08-03 | 70 | Sea | 2022-08-15 | 2022-08-15 | Anel Valdez | HIT | 70 | Open |  | 2022-08-15 | 0 | 0 | 0 | 0
WMKHOU | 999116373 | 1 | 1119917 | FULCRUM | 2022-07-20 | 135 | Sea | 2022-07-30 | 2022-08-15 | Melissa Gonzalez | HIT | 135 | Open |  | 2022-08-15 | 0 | 0 | 0 | 0
WMKHOU | 999116373 | 2 | 1119917 | FULCRUM | 2022-07-20 | 135 | Sea | 2022-08-30 | 2022-08-15 | Melissa Gonzalez | HIT | 135 | Open |  | 2022-08-15 | 0 | 0 | 0 | 0
WMKHOU | 999115477 | 1 | 1156157 | BODY PILOT | 2022-07-01 | 455 | Sea | 2022-07-30 | 2022-08-30 | Melissa Gonzalez | HIT | 455 | Open |  | 2022-08-30 | 0 | 0 | 0 | 0
WMKHOU | 999115477 | 2 | 1156157 | BODY PILOT | 2022-07-01 | 140 | Sea | 2022-07-30 | 2022-08-30 | Melissa Gonzalez | HIT | 140 | Open |  | 2022-08-30 | 0 | 0 | 0 | 0
WMKHOU | 999115477 | 3 | 1156157 | BODY PILOT | 2022-07-01 | 25 | Sea | 2022-07-30 | 2022-08-30 | Melissa Gonzalez | HIT | 25 | Open |  | 2022-08-30 | 0 | 0 | 0 | 0
WMKHOU | 999115147 | 1 | 1120664 | DIAPH. HEAD | 2022-06-28 | 30 | Exp | 2022-06-29 | 2022-07-01 | Melissa Gonzalez | HIT | 0 | Delivered |  | 2022-07-01 | EWL2216 | 30 | 2022-06-30 | E | EWL2216 | 30 | 2022-06-30 | E | UPS | 1Z74Y7096796122054
WMKHOU | 999115086 | 1A | 1124203 | SPRING GUIDE, 1"RV | 2022-06-27 | 500 | Exp | 2022-07-07 | 2022-07-11 | Melissa Gonzalez | HIT | 0 | Delivered |  | 2022-07-11 | EWL2218 | 500 | 2022-07-05 | E | EWL2218 | 500 | 2022-07-05 | E | UPS
WMKHOU | 999115086 | 1B | 1124203 | SPRING GUIDE, 1"RV | 2022-06-27 | 500 | Exp | 2022-07-07 | 2022-07-11 | Melissa Gonzalez | HIT | 0 | Delivered |  | 2022-07-11 | EWL2219 | 500 | 2022-07-07 | E | EWL2219 | 500 | 2022-07-07 | E | UPS
WMKHOU | 999114846 | 1 | 1121900 | ADJ. SCREW, 1"RV | 2022-06-21 | 500 | Exp | 2022-06-22 | 2022-06-22 | Melissa Gonzalez | HIT | 0 | Delivered |  | 2022-06-22 | EWL2215 | 500 | 2022-06-22 | E | EWL2215 | 500 | 2022-06-22 | E | UPS
WMKHOU | 999114827 | 1 | 1156157 | BODY PILOT | 2022-06-21 | 1000 | Sea | 2022-10-30 | 2022-10-30 | Melissa Gonzalez | HIT | 1000 | Open |  | 2022-10-30 | 0 | 0 | 0 | 0
WMKHOU | 999114827 | 2 | 1040326 | BODY PILOT EVIROSAVE | 2022-06-21 | 1000 | Sea | 2022-07-30 | 2022-07-30 | Melissa Gonzalez | HIT | 1000 | Open |  | 2022-07-30 | 0 | 0 | 0 | 0
WMKHOU | 999110316 | 1 | 1119218 | DIAPHRAGM LIMITER | 2022-04-01 | 10 | Sea | 2022-04-07 | 2022-04-12 | Ashlee Tobola | XY | -5 | Delivered |  | 2022-04-12 | XY2206 | 15 | 2022-04-09 | E | XY2206 | 15 | 2022-04-09 | E | UPS | 1Z30952E0424592083
WMKHOU | 999110056 | 1 | 1117875 | SPRING SEAT, P.R. | 2022-03-29 | 500 | Exp | 2022-07-25 | 2022-07-25 | Atrayee Dutta | ML | 0 | Delivered |  | 2022-07-25 | ML220420-2 | 500 | 2022-04-20 | E | ML220420-2 | 500 | 2022-04-20 | E | UPS
WMKHOU | 999109598 | 1 | 1119564 | BOTTOM OFFSHORE PILOT LLC | 2022-03-22 | 500 | Sea | 2022-07-30 | 2022-06-30 | Atrayee Dutta | HIT | 0 | Shipped |  | 2022-07-30 | EWL2217 | 500 | 2022-06-30 | S | EWL2217 | 500 | 2022-06-30 | S
WMKHOU | 999108982 | 1 | 1123589 | PILOT OFFSHORE BODY LLC | 2022-03-11 | 800 | Sea | 2022-06-30 | 2022-06-30 | Atrayee Dutta | HIT | 0 | Shipped |  | 2022-06-30 | EWL2217 | 800 | 2022-06-30 | S | EWL2217 | 800 | 2022-06-30 | S
WMKHOU | 999108982 | 2 | 1117840 | STABILIZER, P.R. | 2022-03-11 | 500 | Exp | 2022-08-25 | 2022-08-25 | Atrayee Dutta | ML | 0 | Delivered |  | 2022-08-25 | ML220802 | 500 | 2022-08-01 | E | ML220802 | 500 | 2022-08-01 | E
WMKHOU | 999108537 | 1 | 1119564 | BOTTOM OFFSHORE PILOT LLC | 2022-03-04 | 500 | Sea | 2022-06-30 | 2022-06-30 | Atrayee Dutta | HIT | 0 | Shipped |  | 2022-06-30 | EWL2217 | 500 | 2022-06-30 | S | EWL2217 | 500 | 2022-06-30 | S
WMKHOU | 999108527 | 1A | 1117823 | UPPER SPRING GUIDE | 2022-03-04 | 250 | Exp | 2022-03-06 | 2022-03-22 | Atrayee Dutta | HIT | 0 | Delivered |  | 2022-03-22 | EWL2212 | 250 | 2022-03-22 | E | EWL2212 | 250 | 2022-03-22 | E
WMKHOU | 999108527 | 1B | 1117823 | UPPER SPRING GUIDE | 2022-03-04 | 250 | Exp | 2022-03-06 | 2022-03-22 | Atrayee Dutta | HIT | 0 | Delivered |  | 2022-03-22 | EWL2212 | 250 | 2022-03-22 | E | EWL2212 | 250 | 2022-03-22 | E
WMKHOU | 999108527 | 1C | 1117823 | UPPER SPRING GUIDE | 2022-03-04 | 250 | Exp | 2022-03-06 | 2022-03-31 | Atrayee Dutta | HIT | 0 | Delivered |  | 2022-03-31 | EWL2213 | 250 | 2022-03-29 | E | EWL2213 | 250 | 2022-03-29 | E
WMKHOU | 999108527 | 1D | 1117823 | UPPER SPRING GUIDE | 2022-03-04 | 250 | Exp | 2022-03-06 | 2022-03-31 | Atrayee Dutta | HIT | 20 | Delivered |  | 2022-03-31 | EWL2213 | 230 | 2022-03-29 | E | EWL2213 | 230 | 2022-03-29 | E
WMKHOU | 999108329 | 1 | 1117840 | STABILIZER, P.R. | 2022-03-02 | 1000 | Exp | 2022-07-25 | 2022-07-25 | Atrayee Dutta | ML | 0 | Delivered |  | 2022-07-25 | ML220802 | 1000 | 2022-08-01 | E | ML220802 | 1000 | 2022-08-01 | E
WMKHOU | 999108329 | 2 | 1117823 | UPPER SPRING GUIDE | 2022-03-02 | 250 | Sea | 2022-04-30 | 2022-04-30 | Atrayee Dutta | HIT | -20 | Shipped |  | 2022-04-30 | EWL2214 | 270 | 2022-04-30 | S | EWL2214 | 270 | 2022-04-30 | S
WMKHOU | 999108056 | 1 | 1123589 | PILOT OFFSHORE BODY LLC | 2022-02-25 | 1000 | Sea | 2022-04-30 | 2022-04-30 | Atrayee Dutta | HIT | 0 | Shipped |  | 2022-04-30 | EWL2214 | 1000 | 2022-04-30 | S | EWL2214 | 1000 | 2022-04-30 | S
WMKHOU | 999108056 | 2 | 1119564 | BOTTOM OFFSHORE PILOT LLC | 2022-02-25 | 500 | Sea | 2022-07-30 | 2022-06-30 | Atrayee Dutta | HIT | 0 | Shipped |  | 2022-07-30 | EWL2217 | 500 | 2022-06-30 | S | EWL2217 | 500 | 2022-06-30 | S
WMKHOU | 999108056 | 3 | 1117840 | STABILIZER, P.R. | 2022-02-25 | 2500 | Exp | 2022-07-25 | 2022-07-25 | Atrayee Dutta | ML | 0 | Delivered |  | 2022-07-25 | ML220420-1 | 2500 | 2022-04-20 | E | ML220420-1 | 2500 | 2022-04-20 | E
WMKHOU | 999108056 | 4A | 1117823 | UPPER SPRING GUIDE | 2022-02-25 | 300 | Exp | 2022-02-28 | 2022-02-28 | Atrayee Dutta | HIT | 0 | Delivered |  | 2022-02-28 | EWL2208 | 300 | 2022-02-27 | E | EWL2208 | 300 | 2022-02-27 | E
WMKHOU | 999108056 | 4B | 1117823 | UPPER SPRING GUIDE | 2022-02-25 | 500 | Sea | 2022-04-30 | 2022-04-30 | Atrayee Dutta | HIT | 0 | Delivered |  | 2022-04-30 | EWL2210 | 500 | 2022-03-10 | E | EWL2210 | 500 | 2022-03-10 | E | UPS
WMKHOU | 999107428 | 1 | 1117854 | LEVER ASSY | 2022-02-16 | 800 | Air | 2022-02-18 | 2022-02-23 | Atrayee Dutta | HIT | 0 | Delivered |  | 2022-02-23 | EWL2204 | 800 | 2022-02-28 | A | EWL2204 | 800 | 2022-02-28 | A
WMKHOU | 999107274 | 1A | 1117854 | LEVER ASSY | 2022-02-14 | 160 | Exp | 2022-02-16 | 2022-02-23 | Atrayee Dutta | HIT | 0 | Delivered |  | 2022-02-23 | EWL2205 | 160 | 2022-02-17 | E | EWL2205 | 160 | 2022-02-17 | E
WMKHOU | 999107274 | 1B | 1117854 | LEVER ASSY | 2022-02-14 | 170 | Exp | 2022-02-16 | 2022-02-23 | Atrayee Dutta | HIT | 0 | Delivered |  | 2022-02-23 | EWL2206 | 170 | 2022-02-20 | E | EWL2206 | 170 | 2022-02-20 | E
WMKHOU | 999107274 | 1C | 1117854 | LEVER ASSY | 2022-02-14 | 170 | Exp | 2022-02-16 | 2022-02-23 | Atrayee Dutta | HIT | 0 | Delivered |  | 2022-02-23 | EWL2207 | 170 | 2022-02-23 | E | EWL2207 | 170 | 2022-02-23 | E
WMKHOU | 999106517 | 1 | 1125204 | BODY 1" SNAPTROL | 2022-02-02 | 50 | Sea | 2022-04-30 | 2022-04-30 | Atrayee Dutta | XY | -20 | Shipped |  | 2022-04-30 | XY2207 | 70 | 2022-05-10 | S | XY2207 | 70 | 2022-05-10 | S
Formulas:
UPDATED = IF([ORIG CFM]="","",[ORIG CFM])
CNTRCT = [SHIP]
Note on B3: Tim: 8/8/2022: changed from 999117319

## ESS
[5 empty] | ORDER | PO | SHIP | REQ. | CFM. | [5 empty] | CNTRCT | CNTRCT | CNTRCT | CNTRCT | 1ST SHIP | 1ST SHIP | 1ST SHIP | 1ST SHIP | 2ND SHIP | 2ND SHIP | 2ND SHIP | 2ND SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | DATE | BUYER | SUPPLIER | BALANCE | STATUS | +/- DAY | NO | QTY | DATE | SV | NO | QTY | DATE | SV | NO | QTY | DATE | SV | NO | QTY | DATE | SV | NO | QTY | DATE | SV

## CEP
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED |  |  |  |  | DELIVERY | ORIG CFM | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIP | SHIPPED | SHIP | SHIPPED | 2ND SHIP | 2ND SHIP | 2ND SHIP | 2ND SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | EXW DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | EXW DATE | NO | QTY | DATE | SV | ID | QTY | DATE | VIA | NO | QTY | DATE | SV | NO | QTY | DATE | SV | NO | QTY | DATE | SV

## BMD
Cust ID | PO # | LN # | P/N | DESCRIPTION | ORDER | PO | SHIP | REQ. | UPDATED | BUYER | SUPPLIER | BALANCE | STATUS | DELIVERY | ORIG CFM | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIP | SHIPPED | SHIP | SHIPPED | FF | TRACKING | SHIP
[5 empty] | DATE | QTY | VIA | DATE | EXW DATE |  |  |  |  | DATE | EXW DATE | NO | QTY | DATE | SV | ID | QTY | DATE | VIA |  |  | DATE
BMD | 15015 | 1 | 61-05-0036 | ADJUSTING SCREW PC10 | 2022-06-10 | 250 | Sea | 2022-07-30 | 2022-07-30 | Shannon Schaper | HIT | 250 | Open |  | 2022-07-30 | 0 | 0 | 0 | 0
BMD | 15015 | 2 | 61-05-0036 | ADJUSTING SCREW PC10 | 2022-06-10 | 250 | Sea | 2022-09-30 | 2022-09-30 | Shannon Schaper | HIT | 250 | Open |  | 2022-09-30 | 0 | 0 | 0 | 0
BMD | 14847 | 1 | 59-05-0057 | LINKAGE W/PIN RG10 | 2022-05-12 | 1000 | Sea | 2022-06-30 | 2022-06-30 | James Bienvenu | HIT | 0 | Shipped |  | 2022-06-30 | EWL2217 | 1000 | 2022-06-30 | S | EWL2217 | 1000 | 2022-06-30 | S
BMD | 14437 | 1 | 61-05-0036 | ADJUSTING SCREW PC10 | 2022-03-03 | 250 | Sea | 2022-03-30 | 2022-03-30 | Burt Boring | HIT | 0 | DELIVERED |  | 2022-03-30 | EWL2214 | 250 | 2022-04-30 | S | EWL2214 | 250 | 2022-04-30 | S
Formulas:
UPDATED = IF([ORIG CFM]="","",[ORIG CFM])

## GRC
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED |  |  |  |  | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIPMENT | QTY | SHIP | SHIPPED |  | FREIGHT | FORWARDER | FORWARDER
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | CFM. DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | CFM. DATE | NO | QTY | DATE | SV | ID | SHIPPED | DATE | VIA | ETA | FORWARDER | SHIPMENT ID | ID NO.
GRC | 4500293992 | 1 | 089-0378-00 | CAP SHPNG MACH SEAL 400 | 2022-05-23 | 500 | Sea | 2022-06-30 | 2022-06-30 | Frank Miranda | XY | -42 | Shipped |  | 2022-06-30 | XY2211 | 542 | 2022-06-30 | S | XY2211 | 542 | 2022-06-30 | S
GRC | 4500292537 | 1 | 089-0378-00 | CAP SHPNG MACH SEAL 400 | 2022-04-27 | 500 | Sea | 2022-05-30 | 2022-05-30 | Frank Miranda | XY | 20 | Shipped |  | 2022-06-15 | XY2208 | 480 | 2022-05-30 | S | XY2208 | 480 | 2022-05-30 | S
GRC | 4500291917 | 1 | 089-0378-00 | CAP SHPNG MACH SEAL 400 | 2022-04-19 | 730 | Sea | 2022-05-30 | 2022-05-30 | Frank Miranda | XY | -14 | Shipped |  | 2022-06-30 | XY2208 | 744 | 2022-05-30 | S | XY2208 | 744 | 2022-05-30 | S
GRC | 4500289295 | 1 | 089-0378-00 | CAP SHPNG MACH SEAL 400 | 2022-03-11 | 500 | Sea | 2022-04-30 | 2022-04-30 | Frank Miranda | XY | -28 | Shipped |  | 2022-04-30 | XY2207 | 528 | 2022-05-10 | S | XY2207 | 528 | 2022-05-10 | S
GRC | 4500288307 | 1 | 089-0378-00 | CAP SHPNG MACH SEAL 400 | 2022-02-23 | 500 | Sea | 2022-04-15 | 2022-04-15 | Frank Miranda | XY | -10 | Delivered |  | 2022-04-15 | XY2205 | 510 | 2022-03-15 | S | XY2205 | 510 | 2022-03-15 | S
Formulas:
UPDATED = IF([ORIG.]="","",[ORIG.])
CNTRCT = [SHIP]

## MB
Cust ID | PO # | LN # | P/N | DESCRIPTION | ORDER | PO | SHIP | REQ. | UPDATED | BUYER | SUPPLIER | BALANCE | STATUS | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIPMENT | QTY | SHIP | SHIPPED |  | FREIGHT | FORWARDER | FORWARDER
[5 empty] | DATE | QTY | VIA | DATE | CFM. DATE |  |  |  |  | DATE | CFM. DATE | NO | QTY | DATE | SV | ID | SHIPPED | DATE | VIA | ETA | FORWARDER | SHIPMENT ID | ID NO.
MB | P54421 | 1 | 634226001 | HAMMER NUT 8" ACME | 2022-07-22 | 1000 | Sea | 2022-08-30 | 2022-08-30 | Jacob Norris | XY | 1000 | Open |  | 2022-08-30 | 0 | 0 | 0 | 0
MB | P54378 | 1 | 634225000 | HAMMER UNION 4" ACME THRD P8700 | 2022-07-18 | 350 | Sea | 2022-07-30 | 2022-08-30 | Jacob Norris | XY | 350 | Open |  | 2022-08-30 | 0 | 0 | 0 | 0
MB | P54054 | 1 | 604283001 | BONNET P8000 | 2022-06-22 | 250 | Sea | 2022-08-30 | 2022-08-30 | Deb McCartney | XY | 250 | Open |  | 2022-08-30 | 0 | 0 | 0 | 0
MB | P53079 | 1 | 664612000 | BODY 1" NPT GLOBE P7200 | 2022-04-05 | 500 | Sea | 2022-05-30 | 2022-07-30 | Deb McCartney | XY | 500 | Open |  | 2022-07-30 | 0 | 0 | 0 | 0
MB | P53026 | 1 | 634232000 | HAMMER UNION 5" ACME P8500 | 2022-04-01 | 500 | Sea | 2022-06-30 | 2022-05-30 | Debbie McCartney | XY | 11 | Shipped |  | 2022-06-30 | XY2208 | 489 | 2022-05-30 | S | XY2208 | 489 | 2022-05-30 | S
MB | P52961 | 1 | 619076000 | P4200 DISK | 2022-03-28 | 1000 | Sea | 2022-06-30 | 2022-06-30 | Debbie McCartney | XY | -62 | Delivered |  | 2022-06-30 | XY2207 | 1062 | 2022-05-10 | S | XY2207 | 1062 | 2022-05-10 | S
MB | P52738 | 1 | 634232000 | HAMMER UNION 5" ACME P8500 | 2022-03-09 | 250 | Sea | 2022-05-30 | 2022-05-30 | Debbie McCartney | XY | -8 | Delivered |  | 2022-05-30 | XY2207 | 258 | 2022-05-10 | S | XY2207 | 258 | 2022-05-10 | S
MB | P52686 | 1 | 664610000 | BODY 4" MACH P8700 | 2022-03-08 | 250 | Sea | 2022-04-30 | 2022-05-30 | Debbie McCartney | XY | -23 | Shipped |  | 2022-05-15 | XY2208 | 273 | 2022-05-30 | S | XY2208 | 273 | 2022-05-30 | S
MB | P52396 | 1A | 634225000 | HAMMER UNION 4" ACME THRD P8700 | 2022-02-11 | 87 | Sea | 2022-03-31 | 2022-04-30 | Debbie McCartney | XY | 0 | Delivered |  | 2022-04-30 | XY2207 | 87 | 2022-05-10 | S | XY2207 | 87 | 2022-05-10 | S
MB | P52396 | 1B | 634225000 | HAMMER UNION 4" ACME THRD P8700 | 2022-02-11 | 163 | Sea | 2022-03-31 | 2022-05-30 | Debbie McCartney | XY | -98 | Shipped |  | 2022-04-30 | XY2208 | 261 | 2022-05-30 | S | XY2208 | 261 | 2022-05-30 | S
MB | P52252 | 1 | 634232000 | HAMMER UNION 5" ACME P8500 | 2022-02-02 | 250 | Sea | 2022-03-30 | 2022-04-30 | Debbie McCartney | XY | -10 | Delivered |  | 2022-04-30 | XY2207 | 260 | 2022-05-10 | S | XY2207 | 260 | 2022-05-10 | S
Formulas:
UPDATED = IF([ORIG.]="","",[ORIG.])
CNTRCT = [SHIP]

## PEL
[5 empty] | ORDER | PO | SHIP | REQ. | CFM. |  |  |  |  | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIP | SHIPPED | SHIP | SHIPPED | 2ND SHIP | 2ND SHIP | 2ND SHIP | 2ND SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | CFM. DATE | NO | QTY | DATE | SV | ID | QTY | DATE | VIA | NO | QTY | DATE | SV | NO | QTY | DATE | SV | NO | QTY | DATE | SV

## PA
[5 empty] | ORDER | PO | SHIP | REQ. | CFM. | [5 empty] | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIP | SHIPPED | SHIP | SHIPPED | 2ND SHIP | 2ND SHIP | 2ND SHIP | 2ND SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | DATE | BUYER | SUPPLIER | BALANCE | STATUS | delivery date | CFM. DATE | NO | QTY | DATE | SV | ID | QTY | DATE | VIA | NO | QTY | DATE | SV | NO | QTY | DATE | SV | NO | QTY | DATE | SV
PA | 7-2209 | 1 | 72501-01 | GAS NOZZLE PLAIN 3/4"NPT GS | 2022-08-01 | 140 | Sea | 2022-08-30 | 2022-09-15 | Joel Shadday | HIT | 140 | Open |  | 2022-09-15 | 0 | 0 | 0 | 0
PA | 7-2209 | 2 | 72404-30 | 3-5/8" CUP MATTE POLISHED GS | 2022-08-01 | 100 | Sea | 2022-08-30 | 2022-09-15 | Joel Shadday | HIT | 100 | Open |  | 2022-09-15 | 0 | 0 | 0 | 0
PA | 7-2209 | 3 | 72013 | 7-3/4" RING GS | 2022-08-01 | 50 | Sea | 2022-08-30 | 2022-08-30 | Joel Shadday | XY | 50 | Open |  | 2022-09-15 | 0 | 0 | 0 | 0
PA | 7-2209 | 4 | 72004A-02 | BRACKET 5-1/2" MATTE GS | 2022-08-01 | 40 | Sea | 2022-08-30 | 2022-09-15 | Joel Shadday | HIT | 40 | Open |  | 2022-09-15 | 0 | 0 | 0 | 0
PA | 7-2209 | 5 | 72707-20 | RING BASE 7-1/2" MATTE POLISHED GS | 2022-08-01 | 50 | Sea | 2022-08-30 | 2022-09-15 | Joel Shadday | HIT | 50 | Open |  | 2022-09-15 | 0 | 0 | 0 | 0
PA | 7-2209 | 6 | 72006-02 | 6" BOWLER BASE MATTE POLISHED GS | 2022-08-01 | 50 | Sea | 2022-08-30 | 2022-09-15 | Joel Shadday | HIT | 50 | Open |  | 2022-09-15 | 0 | 0 | 0 | 0
PA | J051422 | 1 | 72404-30 | 3-5/8" CUP MATTE POLISHED W/T | 2022-05-14 | 100 | Sea | 2022-05-30 | 2022-06-30 | Joel Shadday | HIT | -5 | Shipped |  | 2022-06-30 | EWL2217 | 105 | 2022-06-30 | S | EWL2217 | 105 | 2022-06-30 | S
PA | J051422 | 2 | 72005 | SUPPORT WALL BRACKET 9" W/T | 2022-05-14 | 60 | Sea | 2022-05-30 | 2022-06-30 | Joel Shadday | HIT | 0 | Shipped |  | 2022-06-30 | EWL2217 | 60 | 2022-06-30 | S | EWL2217 | 60 | 2022-06-30 | S
PA | J051422 | 3 | 72004A | BRACKET 5-1/2" W/T | 2022-05-14 | 60 | Sea | 2022-05-30 | 2022-06-30 | Joel Shadday | HIT | 0 | Shipped |  | 2022-06-30 | EWL2217 | 60 | 2022-06-30 | S | EWL2217 | 60 | 2022-06-30 | S
PA | JOEL030922 | 1 | 72210 | 8" LAMP BASE W/T | 2022-03-09 | 500 | Sea | 2022-03-30 | 2022-04-30 | Joel Shadday | HIT | 0 | Shipped |  | 2022-04-30 | EWL2214 | 500 | 2022-04-30 | S | EWL2214 | 500 | 2022-04-30 | S
PA | JOEL020222 | 1 | 72202-00 | 3-3/4" LAMP BASE PLAIN W/T | 2022-02-02 | 200 | Sea | 2022-02-28 | 2022-03-31 | Joel Shadday | HIT | 0 | Shipped |  | 2022-03-31 | EWL2214 | 200 | 2022-04-30 | S | EWL2214 | 200 | 2022-04-30 | S
PA | JOEL011022 | 1 | 72100 | 6" RING BASE W/T | 2022-01-10 | 400 | Sea | 2022-01-30 | 2022-03-30 | Joel Shadday | HIT | -100 | Shipped |  | 2022-02-28 | EWL2214 | 500 | 2022-04-30 | S | EWL2214 | 500 | 2022-04-30 | S
Formulas:
DATE = IF([CFM. DATE]="","",[CFM. DATE])

## PSM
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED |  |  |  |  | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIPMENT | QTY | SHIP | SHIP |  | FREIGHT | FORWARDER | FORWARDER
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | CFM. DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | CFM. DATE | NO | QTY | DATE | SV | ID | SHIPPED | DATE | VIA | ETA | FORWARDER | SHIPMENT ID | ID NO.

## HL
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED |  |  |  |  | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIPMENT | QTY | SHIP | SHIP |  | FREIGHT | FORWARDER | FORWARDER
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | CFM. DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | CFM. DATE | NO | QTY | DATE | SV | ID | SHIPPED | DATE | VIA | ETA | FORWARDER | SHIPMENT ID | ID NO.

## DMI
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED |  |  |  |  | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIPMENT | QTY | SHIP | SHIPPED |  | FREIGHT | FORWARDER | FORWARDER
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | CFM. DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | CFM. DATE | NO | QTY | DATE | SV | ID | SHIPPED | DATE | VIA | ETA | FORWARDER | SHIPMENT ID | ID NO.

## MM
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED |  |  |  |  | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIPMENT | QTY | SHIP | SHIPPED |  | FREIGHT | FORWARDER | FORWARDER
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | CFM. DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | CFM. DATE | NO | QTY | DATE | SV | ID | SHIPPED | DATE | VIA | ETA | FORWARDER | SHIPMENT ID | ID NO.
MM | 2239 | 1 | EA-8888 | MOUNT FOOT STD W/T | 2022-04-19 | 500 | Sea | 2022-04-30 | 2022-06-30 | Andre Cokinos | HIT | 0 | Shipped |  | 2022-05-30 | EWL2217 | 500 | 2022-06-30 | S | EWL2217 | 500 | 2022-06-30 | S
Formulas:
CNTRCT = [SHIP]

## SES
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED |  |  |  |  | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIPMENT | QTY | SHIP | SHIP |  | FREIGHT | FORWARDER | FORWARDER
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | CFM. DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | CFM. DATE | NO | QTY | DATE | SV | ID | SHIPPED | DATE | VIA | ETA | FORWARDER | SHIPMENT ID | ID NO.

## VEI
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED |  |  |  |  | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIPMENT | QTY | SHIP | SHIPPED |  | FREIGHT | FORWARDER | FORWARDER
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | CFM. DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | CFM. DATE | NO | QTY | DATE | SV | ID | SHIPPED | DATE | VIA | ETA | FORWARDER | SHIPMENT ID | ID NO.

## AMC
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED |  |  |  |  | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIPMENT | QTY | SHIP | SHIPPED |  | FREIGHT | FORWARDER | FORWARDER
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | CFM. DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | CFM. DATE | NO | QTY | DATE | SV | ID | SHIPPED | DATE | VIA | ETA | FORWARDER | SHIPMENT ID | ID NO.

## OKS
Cust ID | PO # | LN # | P/N | DESCRIPTION | ORDER | PO | SHIP | REQ. | UPDATED | BUYER | SUPPLIER | BALANCE | STATUS | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIPMENT | QTY | SHIP | SHIPPED |  | FREIGHT | TRACKING | FORWARDER | FORWARDER
[5 empty] | DATE | QTY | VIA | DATE | CFM. DATE |  |  |  |  | DATE | CFM. DATE | NO | QTY | DATE | SV | ID | SHIPPED | DATE | VIA | ETA | FORWARDER | NUMBER | SHIPMENT ID | ID NO.
OKS | 72522 | 1 | 07-0042 | PADDLE LONG FINGER | 2022-07-27 | 600 | Sea | 2022-09-30 | 2022-09-30 | Erin Wheeler | XY | 600 | Open |  | 2022-09-30 | 0 | 0 | 0 | 0
OKS | 72522 | 2 | 07-0042 | PADDLE LONG FINGER | 2022-07-27 | 600 | Sea | 2023-02-28 | 2023-02-28 | Erin Wheeler | XY | 600 | Open |  | 2023-02-28 | 0 | 0 | 0 | 0
OKS | 71222 | 1 | 120-75-19A | PADDLE-SHAFT-PIN ASSEMBLY SAMPLE | 2022-07-12 | 5 | Exp | 2022-07-30 | 2022-08-15 | Erin Wheeler | XY | 5 | Open |  | 2022-08-15 | 0 | 0 | 0 | 0
OKS | 71222 | 2 | 120-75-19A | PADDLE-SHAFT-PIN ASSEMBLY | 2022-07-12 | 100 | Air | 2022-08-15 |  | Erin Wheeler | XY | 100 | Open |  |  | 0 | 0 | 0 | 0
OKS | 71222 | 3 | 120-75-19A | PADDLE-SHAFT-PIN ASSEMBLY | 2022-07-12 | 100 | Sea | 2022-08-15 |  | Erin Wheeler | XY | 100 | Open |  |  | 0 | 0 | 0 | 0
OKS | 61722 | 1 | 1125960 | CAP | 2022-06-17 | 250 | Sea | 2022-06-30 | 2022-06-30 | Judy Wheeler | XY | -19 | Shipped |  | 2022-06-30 | XY2211 | 269 | 2022-06-30 | S | XY2211 | 269 | 2022-06-30 | S
OKS | 61722 | 2 | 1120626 | SCREW ADJUSTING | 2022-06-17 | 250 | Sea | 2022-06-30 | 2022-06-30 | Judy Wheeler | HIT | 0 | Shipped |  | 2022-06-30 | EWL2217 | 250 | 2022-06-30 | S | EWL2217 | 250 | 2022-06-30 | S
OKS | 60222 | 1 | 1149288 | COVER | 2022-06-02 | 800 | Sea | 2022-07-30 | 2022-07-30 | Judy Wheeler | HIT | 0 | Shipped |  | 2022-07-30 | EWL2217 | 800 | 2022-06-30 | S | EWL2217 | 800 | 2022-06-30 | S
OKS | 52622 | 1 | 1120626 | SCREW ADJUSTING | 2022-05-26 | 200 | Exp | 2022-05-29 | 2022-06-02 | Judy Wheeler | HIT | 0 | Delivered |  | 2022-06-02 | EWL2215 | 200 | 2022-06-02 | E | EWL2215 | 200 | 2022-06-02 | E
OKS | 52622 | 2 | 1120626 | SCREW ADJUSTING | 2022-05-26 | 470 | Sea | 2022-06-30 | 2022-06-30 | Judy Wheeler | HIT | 0 | Shipped |  | 2022-06-30 | EWL2217 | 470 | 2022-06-30 | S | EWL2217 | 470 | 2022-06-30 | S
OKS | 52022 | 1 | 1121130 | COLLAR FOR 1800-LLC | 2022-05-20 | 100 | Exp | 2022-05-27 | 2022-05-29 | Judy Wheeler | XY | -40 | Delivered |  | 2022-05-29 | XY2209 | 140 | 2022-06-02 | E | XY2209 | 140 | 2022-06-02 | E
OKS | 31522 | 1 | 1125960 | CAP | 2022-03-16 | 200 | Sea | 2022-03-30 | 2022-04-15 | Erin Wheeler | XY | -13 | Delivered |  | 2022-04-15 | XY2207 | 213 | 2022-05-10 | S | XY2207 | 213 | 2022-05-10 | S
OKS | 31522 | 2 | 1120626 | SCREW ADJUSTING | 2022-03-16 | 200 | Sea | 2022-03-30 | 2022-03-30 | Erin Wheeler | HIT | 0 | Delivered |  | 2022-03-30 | EWL2214 | 200 | 2022-04-30 | S | EWL2214 | 200 | 2022-04-30 | S
OKS | 31522 | 3 | 1117864 | CONNECTOR | 2022-03-16 | 100 | Sea | 2022-03-30 | 2022-03-30 | Erin Wheeler | HIT | 0 | Delivered |  | 2022-03-30 | EWL2214 | 100 | 2022-04-30 | S | EWL2214 | 100 | 2022-04-30 | S
OKS | 31522 | 4 | 1149272 | ECCENTRIC WHEEL | 2022-03-16 | 200 | Sea | 2022-03-30 | 2022-04-15 | Erin Wheeler | XY | -28 | Delivered |  | 2022-04-15 | XY2207 | 228 | 2022-05-10 | S | XY2207 | 228 | 2022-05-10 | S
OKS | 31022 | 1 | 1117864 | CONNECTOR | 2022-03-10 | 220 | Exp | 2022-03-11 | 2022-03-11 | Judy Wheeler | HIT | 0 | Delivered |  | 2022-03-11 | EWL2209 | 220 | 2022-03-11 | E | EWL2209 | 220 | 2022-03-11 | E |  | UPS
OKS | 12222 | 1 | 07-0032 | SLURRY CUP SLEEVE | 2022-01-22 | 300 | Exp | 2022-02-15 | 2022-02-28 | Judy Wheeler | XY | -4 | Delivered |  | 2022-02-28 | XY2204 | 304 | 2022-03-01 | E | XY2204 | 304 | 2022-03-01 | E |  | DHL | 3736542316
OKS | 11922 | 1 | 1149288 | COVER | 2022-01-19 | 200 | Exp | 2022-01-21 | 2022-01-30 | Judy Wheeler | HIT | 0 | Delivered |  | 2022-01-30 | EWL2202 | 200 | 2022-01-25 | E | EWL2202 | 200 | 2022-01-25 | E
OKS | 11022 | 1 | 1117864 | CONNECTOR | 2022-01-10 | 250 | Sea | 2022-01-30 | 2022-02-28 | Judy Wheeler | HIT | 0 | Delivered |  | 2022-02-28 | EWL2214 | 250 | 2022-04-30 | S | EWL2214 | 250 | 2022-04-30 | S
OKS | 11022 | 2 | 1120626 | SCREW ADJUSTING | 2022-01-10 | 250 | Sea | 2022-01-30 | 2022-02-28 | Judy Wheeler | HIT | 0 | Delivered |  | 2022-02-28 | EWL2214 | 250 | 2022-04-30 | S | EWL2214 | 250 | 2022-04-30 | S
Formulas:
UPDATED = IF([ORIG.]="","",[ORIG.])

## NG
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED |  |  |  |  | DELIVERY | ORIG CFM | CNTRCT | CNTRCT | CNTRCT | CNTRCT | 1ST SHIP | 1ST SHIP | 1ST SHIP | 1ST SHIP | 2ND SHIP | 2ND SHIP | 2ND SHIP | 2ND SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | EXW DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | EXW DATE | NO | QTY | DATE | SV | NO | QTY | DATE | SV | NO | QTY | DATE | SV | NO | QTY | DATE | SV | NO | QTY | DATE | SV

## GQS
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED |  |  |  |  | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | 1ST SHIP | 1ST SHIP | 1ST SHIP | 1ST SHIP | FREIGHT | FORWARDER | FORWARDER
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | CFM. DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | CFM. DATE | NO | QTY | DATE | SV | NO | QTY | DATE | SV | FORWARDER | SHIPMENT ID | ID NO.

## SFE
[5 empty] | ORDER | PO | SHIP | REQ. | CFM. | [5 empty] | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | SHIP | SHIPPED | SHIP | SHIPPED | 2ND SHIP | 2ND SHIP | 2ND SHIP | 2ND SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 3RD SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP | 4TH SHIP
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | DATE | BUYER | SUPPLIER | BALANCE | STATUS | +/- DAY | CFM. DATE | NO | QTY | DATE | SV | ID | QTY | DATE | VIA | NO | QTY | DATE | SV | NO | QTY | DATE | SV | NO | QTY | DATE | SV
SFE | 10560 | 1 | 05.0550.016A | BRUSH, DC DRIVE MOTOR | 2022-01-08 | 50 | Exp | 2022-01-14 |  | Niki Teague | BKT | 0 | Open |  |  | TOP201602A | 50 | 2022-01-15 | E | TOP201602A | 50 | 2022-01-15 | E | FEDEX
Formulas:
DATE = [DATE]

## Others
[5 empty] | ORDER | PO | SHIP | REQ. | UPDATED |  |  |  |  | DELIVERY | ORIG. | CNTRCT | CNTRCT | CNTRCT | CNTRCT | 1ST SHIP | 1ST SHIP | 1ST SHIP | 1ST SHIP | FREIGHT | FORWARDER | FORWARDER
Cust ID | PO # | LN # | P/N | DESCRIPTION | DATE | QTY | VIA | DATE | CFM. DATE | BUYER | SUPPLIER | BALANCE | STATUS | DATE | CFM. DATE | NO | QTY | DATE | SV | NO | QTY | DATE | SV | FORWARDER | SHIPMENT ID | ID NO.